## GanttChart
Grantt Chart - Project
website for ‘Loftus frukt og saft’
| START DAY | 2020-10-26 |  |  | FINISH DAY | 11-30-2020 | 1 |  | week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4 | [6 empty] | week 5 | [6 empty] | week 6 | [6 empty] | week 7 | [6 empty] | week 8
| PROJECT MENAGER | Bart Gaj | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14
 | time axis 2020-10-26 to 2020-12-20
|  | People Assign | People Assigned | Start | Finish | Days | % work done | work-days | time axis 2020-10-26 to 2020-12-20
1 | Approval of the project |  |  |  | - |  |  | -
1.1 | Establishing a Plan, Team meeting | All team |  | 2020-10-26 | 2020-10-27 | 2 | 50% | 2
2 | Main Layout | 28/10/20 - 8/11/20 |  |  | - |  |  | -
2.1 | Research - Page Features | UI/UX |  | 2020-10-28 | 2020-10-29 | 2 | 100% | 2
2.2 | Collect Client's Vision and Goals | UI/UX + PM |  | 2020-10-28 | 2020-10-29 | 2 | 100% | 2
2.3 | Request Client Moodboard | UI/UX |  | 2020-10-28 | 2020-10-29 | 2 | 100% | 2
2.4 | Design Concepts | UI/UX |  | 2020-10-30 | 2020-11-03 | 5 | 0% | 3
2.5 | Content and Material | UI/UX |  | 2020-10-28 | 2020-10-30 | 3 | 80% | 3
2.6 | Technical Drawings-Pictures | UI/UX |  | 2020-10-29 | 2020-11-03 | 6 | 20% | 4
2.7 | Color and Graphics | UI/UX |  | 2020-10-29 | 2020-11-02 | 5 | 20% | 3
2.8 | Review with Marketing | UI/UX + PM |  | 2020-10-30 | 2020-10-30 | 1 | 0% | 1
2.9 | Webepage Design Mockup Complet Checking | UI/UX + PM |  | 2020-11-02 | 2020-11-05 | 4 | 0% | 4
2.10 | Approval the complete site | UI/UX + PM |  | 2020-11-04 | 2020-11-07 | 4 | 0% | 3
3 | Build | 9/11/20-22/11/20 |  |  | - |  |  | -
3.1 | Setup Servers - Database | Developer |  | 2020-11-09 | 2020-11-10 | 2 | 0% | 2
3.2 | Set up website customization | Developer |  | 2020-11-10 | 2020-11-12 | 3 | 0% | 3
3.3 | Payment gateway Integration | Developer |  | 2020-11-11 | 2020-11-12 | 2 | 0% | 2
3.4 | Ordering form spec | Developer |  | 2020-11-12 | 2020-11-13 | 2 | 0% | 2
3.5 | Build Template Design | Developer |  | 2020-11-13 | 2020-11-17 | 5 | 0% | 3
3.6 | Tools and Technology | Developer |  | 2020-11-10 | 2020-11-14 | 5 | 0% | 4
3.7 | Mobile APP structure | Developer |  | 2020-11-10 | 2020-11-21 | 12 | 0% | 9
3.8 | Programming | Developer |  | 2020-11-16 | 2020-11-20 | 5 | 0% | 5
3.9 | Copywriting | Copywriter |  | 2020-11-17 | 2020-11-21 | 5 | 0% | 4
4 | Testing | 23/11/20-28/11/20 |  |  | - |  |  | -
4.1 | The visitor-customer flow | Developer |  | 2020-11-23 | 2020-11-24 | 2 | 0% | 2
4.2 | The Functionalities | Developer |  | 2020-11-23 | 2020-11-25 | 3 | 0% | 3
4.3 | Secruity | Developer |  | 2020-11-24 | 2020-11-26 | 3 | 0% | 3
4.4 | Technical Issue -Analytics | QA enginner |  | 2020-11-24 | 2020-11-25 | 2 | 0% | 2
4.5 | Complete checking and debuging | QA enginner |  | 2020-11-25 | 2020-11-26 | 2 | 0% | 2
4.6 | Implementation | Developer |  | 2020-11-26 | 2020-11-26 | 1 | 0% | 1
5 | Social Marketing | 9/11/20-20/11/20 |  |  | - |  |  | -
5.1 | Advertisement | Marketing Strategist |  | 2020-11-09 | 2020-11-10 | 2 | 0% | 2
5.2 | Adwords | Marketing Strategist |  | 2020-11-10 | 2020-11-11 | 2 | 0% | 2
5.3 | Facebook | Marketing Strategist |  | 2020-11-12 | 2020-11-12 | 1 | 0% | 1
5.4 | Instagram | Marketing Strategist |  | 2020-11-12 | 2020-11-12 | 1 | 0% | 1
5.5 | Youtube | Marketing Strategist |  | 2020-11-12 | 2020-11-12 | 1 | 0% | 1
5.6 | User Experience | Marketing Strategist |  | 2020-11-13 | 2020-11-15 | 3 | 0% | 1
5.7 | Promotion | Marketing Strategist |  | 2020-11-13 | 2020-11-15 | 3 | 0% | 1
5.8 | Target Market | Marketing Strategist |  | 2020-11-16 | 2020-11-18 | 3 | 0% | 3
5.9 | Expectations | MS + PM |  | 2020-11-17 | 2020-11-18 | 2 | 0% | 2
5.10 | Objectives | MS + PM |  | 2020-11-18 | 2020-11-19 | 2 | 0% | 2
6 | Meetings |  |  |  | - |  |  | -
6.1 | Team kick-off meeting | All team |  | 2020-11-10 | 2020-11-10 | 1 | 0% | 1
6.2 | Meeting with Client | PM Project Menager |  | 2020-11-09 | 2020-11-09 | 1 | 0% | 1
6.3 | Summary Meeting | PM Project Menager |  | 2020-11-27 | 2020-11-27 | 1 | 0% | 1
7 | Finallize the Project | 27/11/20-30/11/20 |  |  | - |  |  | -
7.1 | Ending-Final Report | Dev + PM |  | 2020-11-27 | 2020-11-27 | 1 | 0% | 1
7.2 | Launching fully working site | Developer |  | 2020-11-30 | 2020-11-30 | 1 | 0% | 1
Formulas:
week 1 = [week 1, row below]
week 2 = [week 2, row below]
week 3 = [week 3, row below]
week 4 = [week 4, row below]
week 5 = [week 5, row below]
week 6 = [week 6, row below]
week 7 = [week 7, row below]
week 8 = [week 8, row below]
work-days = IF(OR([FINISH DAY]=0,[Start]=0)," - ",NETWORKDAYS([Start],[FINISH DAY]))
FINISH DAY = IF(ISBLANK([Start])," - ",IF([Days]=0,[Start],[Start]+[Days]-1))
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.